## Leo's Timesheet
Date | Day of The Week | Description | Hours | Running Total
2019-07-01 | Monday | Build Web Site Template in Visual Studio. | 3 | 3
2019-07-02 | Tuesday | Finalizing the site template | 2 | 5
2019-07-03 | Wednesday | Researching various graphic editing tools for the project. | 2 | 7
2019-07-04 | Thursday | Finalizing the graphic tools research. The best tool is InkScape | 1 | 8
2019-07-05 | Friday | Taking some training in InkScape for developing vector images and maps | 3 | 11
2019-07-06 | Saturday | Drafting/started design of campus map in InkScape, added website features like scrolling and popups | 6 | 17
2019-07-07 | Sunday | Screen capturing fire maps | 4 | 21
2019-07-08 | Monday | Creating floor6 template | 2 | 23
2019-07-09 | Tuesday | Verifying floor6 template in the hospital | 2 | 25
2019-07-10 | Wednesday | Editing floor diagram | 3 | 28
2019-07-11 | Thursday | Started creating floor 5 | 1 | 29
2019-07-12 | Friday | Editing floor diagram | 3 | 32
2019-07-13 | Saturday | Releasing first images on website, editing view of page and images | 3 | 35
2019-07-14 | Sunday | Started creating floor 4 in Inkscape | 4 | 39
2019-07-15 | Monday | Editing floor diagram | 2 | 41
2019-07-16 | Tuesday | Creating Floor 3 | 2 | 43
2019-07-17 | Wednesday | Editing floor diagram | 2 | 45
2019-07-18 | Thursday | Creating directory listing on website | 1 | 46
2019-07-19 | Friday | Business card creation in InkScape + purchase | 3 | 49
2019-07-20 | Saturday | Started on Floor 1 and editing of image | 5 | 54
2019-07-21 | Sunday | Creating placeholder images on website using filters and art style transfer | 6 | 60
2019-07-22 | Monday | Getting additional information and making corrections | 3 | 63
2019-07-23 | Tuesday | Adjusting color scheme of maps and website to match RWJBH colors | 3 | 66
2019-07-24 | Wednesday | Open Hosting and Deployment | 3 | 69
2019-07-25 | Thursday | Adding additional links/info to website - address, facebook, twitter, linkedin pages, google maps directions | 2 | 71
2019-07-26 | Friday | Domain Registration, finished overall campus map | 3 | 74
2019-07-27 | Saturday | Finish campus map, started and finished ground floor | 6 | 80
2019-07-28 | Sunday | Create PDF file combining all maps upload to the site and wire download button, other javascript work for aesthetics, pickup cards | 5 | 85
2019-07-29 | Monday | Finishing touches on the website, make sure everything functions properly | 1 | 86